## Sheet1
SEVERITY
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Strain injuries | Working for too long may induce strain injury | Get up and move around every now and again | Maintain a reasonable level of comfort while working | Expected | Minimal | 4 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Development time will exceed recommended time | 5 hours is not enough. | Pour more time into it. | Get it done as fast as possible. | Guaranteed | Major | 20 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | Configuration issues | Issues when setting up things we haven't worked with before without proper instruction | Verify online documentation | Try and find solution and tutorials online | Expected | Major | 16 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Balance between work at office and working on project | Extremely difficult week to balance both work and project | Work overtime for multiple days | Escalate concerns | Expected | Major | 16 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | Insufficient project management skills | Documentation, JIRA management, user stories written are not great | Document everything step by step, keep track of everything | Have good documentation which applies to project | Likely | Moderate | 6 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6 | Software failures | Experienced issues using VSCode | Moved to Intellij | Ensured that I could continue development | Possible | Major | 8
7 | Inssufficient Unit Tests | Application prone to bugs | Ensure everything is tested in full | Ensure a safe and bug free application | Possible | Major | 4